## Cover
GASIFICATION DATABASE
PROPOSED U.S. PROJECTS HAVING COMMERCIAL POTENTIAL
The data presented herein has been sourced from: the Internet; literature sources purchased by DOE; and other independent literature sources provided openly to DOE.
2016-06-15

## Introduction
INTRODUCTION
Proposed U.S. Gasification Projects Having Commercial Potential
Welcome to the Department of Energy's (DOE) Office of Fossil Energy (FE) / National Energy Technology Laboratory (NETL) Gasification Database. This Database tracks proposed large-scale gasification projects in the United States (U.S.). Projects are categorized as either "Active," recently "Delayed/Cancelled," or "Other." The "Other" category is defined as projects that have been announced, but for which data are limited. Only domestic, proposed projects are included; currently operating projects (e.g., Tampa Polk, Wabash, etc.) are excluded. This Database presents factual rather than interpretive information. For those instances where conflicting data are found in the supporting literature, the most recently dated information is used.
The data presented herein has been sourced from: publicly available information and internal information approved for public release. Every attempt is made to keep sources updated and accurate. However, if a source or link is found to be invalid, or if you have information that you would like to have included in this database, please notify the database administrators via e-mail: Gasification@netl.doe.gov

## Disclaimer
DISCLAIMER
Proposed U.S. Gasification Projects Having Commercial Potential
This report is intended to provide an overview of proposed new gasification plants that are under development. This report may not represent all possible plants under consideration but is intended to illustrate the potential that exists for installation of new U.S. gasification plants. The Department of Energy does not warrant the accuracy or suitability of this information. Experience has shown that public announcements of gasification plant developments do not provide an accurate representation of eventually commissioned gasification plants. Actual plant capacity commissioned has historically been significantly less than new capacity announced. The report focuses on those gasification projects that have achieved significant progress toward completion, to provide a more accurate assessment of the ability of this segment of the power generation industry to support demand for new electricity capacity in various regions of the world.

## Abbreviations
ABBREVIATIONS AND ACRONYMS
Proposed U.S. Gasification Projects Having Commercial Potential
BCF | Billion Cubic Feet | NETL | National Energy Technology Laboratory
BCFY | Billion Cubic Feet per Year | PC | Pulverized Coal
BPD | Barrels per Day | PPA | Preliminary Project Approval
BTC | Biomass-to-Chemicals | PTL | Petcoke-to-Liquids
BTL | Biomass to Liquids | RFP | Request for Proposals
CBTL | Coal-Biomass-to-Liquids | SCFD | Standard Cubic Feet per Day
CCPI | Clean Coal Power Initiative | SCPC | Supercritical Pulverized Coal
CCS | Carbon Capture and Storage | SNG | Synthetic Natural Gas
CO2 | Carbon Dioxide | TPD | Tons per Day
COE | Cost of Electricity | TPY | Tons per Year
CTC | Coal-to-Chemicals | TRIG | Transport Reactor Integrated Gasifier
CTL | Coal-to-Liquids | WTE | Waste-to-Energy
DOE | Department of Energy (U.S.) | WTEth | Waste-to-Ethanol
EIS | Environmental Impact Statement
EOR | Enhanced Oil Recovery
EPA | Environmental Protection Agency (U.S.)
FE | Fossil Energy (U.S. Department of Energy Office of)
FEED | Front-End Engineering and Design
F-T | Fischer-Tropsch
GPY | Gallons per Year
H2 | Hydrogen
IGCC | Integrated Gasification Combined Cycle
LLC | Limited Liability Company
MOU | Memorandum of Understanding
MTPY | Million Tons per Year
MW | Megawatts

## Projects Summary
U.S. GASIFICATION PROJECTS
| Release date: June 2016 |  | (Note: Projects are listed by type and location in three groups: Active, Delayed or Cancelled, and Other Conceptual Projects.)
PROJECT NAME | LAST UPDATE (Month, YY) | DEVELOPER | CITY OR COUNTY (Counties specificied) | STATE | TYPE | SIZE | COST | STATUS | EMISSIONS CONTROL PLAN | NOTES | INFORMATION SOURCE
Adams Fork Energy - TransGas WV CTL | 2015-09-15 | TransGas Development Systems (TGDS) | Mingo County | West Virginia | CTL | 7,500 TPD of coal to 1 billion gallons/yr gasoline and liquid fuels | $3 billion | A - Active | Not identified; developers hope to get a right of way to send CO2 through interstate pipelines to the Texas coast for EOR | Developers haven't yet locked up financing for a $3 billion plant they say won't be up and running until at least 2016. Acording to company website on the project, the project has received construction and operation permits from the WV Department of Environmental Protection and is presently under construction. The Adams Fork facility will serve as a reference point for the company's Buffalo Creek and Chisolm facilities to be built in KY. While permits have been approved on the facility, there is some question as to whether the permits are still viable as next to no work has been performed at the site for some time. | http://www.eenews.net/greenwire/stories/1059981383 http://www.transgasdevelopment.com/projects/ http://www.mingomessenger.com/news/article_efc96ce6-b3db-11e4-900c-df7269f2855a.html
American Lignite Energy (aka Coal Creek Project) | 2014-08-14 | American Lignite Energy LLC (North American Coal, Headwaters Energy Services) | MacLean County | North Dakota | CTL | 11.5 million TPY lignite coal to 32,000 BPD of undefined fuel | $4 billion | D - Delayed / Cancelled | 70% of CO2 to be used for EOR | Company continues to receive annual extensions to determine if the project will be feasible. Company representatives have stated that the project needs favorable coal legislation in the US as well as a clear energy policy to move forward. | http://www.businessweek.com/ap/2013-11-08/as-nd-coal-projects-languish-some-question-worth
Belwood Coal-to-Liquids Project (Natchez) | 2014-04-08 | Rentech | Natchez | Mississippi | CTL | Petcoke to up to 30,000 BPD ultra-clean diesel | $4.5 billion. The project depends on $2.75 billion in state-issued bonds. | D - Delayed / Cancelled | CO2 takeoff agreement with Denbury Resources for EOR, designed to capture ~80% Life-cycle analysis indicates the proposed plant could lower CO2 emissions 11-23% over conv. petroleum refining. | Rentech, Inc. announced plans to cease operations at, reduce staffing at, and mothball its research and development (R&D) Product Demonstration Unit (PDU), in Commerce City, CO, and to eliminate all related R&D activities. The Company's strategy is focused on more immediate growth opportunities within the energy industry that do not rely on new technologies. According to company filings, Rentech has begun the process of selling the 450 acres it intended to use for its coal-to-liquids Natchez project. The company sold the land to the Adam's County government for $9.25 million in August 2013. | http://phx.corporate-ir.net/phoenix.zhtml?c=66629&p=irol-newsArticle&ID=1790402&highlight= http://www.natchezdemocrat.com/2013/08/16/county-closes-on-rentech-land-sale/
Cabin Creek | 2016-03-01 | Tahoe Regional Power Company | Placer County | California | BTE | 2 MWe | $12 million | A - Active | Not identified | The proposed two-megawatt Cabin Creek Biomass Energy Facility would take state and local agencies’ woody biomass — trees, shrubs and other plants that can come from fire hazard reduction projects — and convert it into energy, with a goal to reduce the threat of local catastrophic wildfires and improve air quality. As the developer, Tahoe Regional Power Company is negotiating with investors for funds to purchase equipment, build the approximately 11,000 square-foot, two-story building, and prepare for operations. Construction is estimated at $12 million, with $1.5 million being funded through Department of Energy grants to the county. The Placer County Board of Supervisors has approved several items related to the project including fuel supply and delivery agreements, an energy sale agreement, and others. Lease agreements for the property have been extended such that the Tahoe Regional Power Company has until July 2017 to complete its Due Diligence Period and finalize power purchase agreements for power produced from the facility. | http://www.tahoedailytribune.com/news/11236082-113/biomass-county-energy-facility http://www.fs.usda.gov/Internet/FSE_DOCUMENTS/stelprdb5393957.pdf http://www.placer.ca.gov/upload/bos/cob/documents/sumarchv/2015/151208A/18b.pdf
Cash Creek Generation | 2015-12-15 | Erora Group | Henderson County | Kentucky | IGCC (via SNG) | 1.7 million TPY coal to SNG and 720 MW electricity | $1.97 billion. Financial commitment received from D.E. Shaw in 10/06. GE Energy acquired 20% of the project in 01/07. | O - Other | Signed a CO2 sales contract with Denbury Resources for EOR; CO2 pipeline may be built to transport CO2 to Texas | In July 2012, the US EPA granted part of and denied part of a petition that requested the US EPA to object to the Cash Creek Title V permit. No additional information has been made public on this project since. In September 2011, the project received a 5 year extension on its conditional use permit from Henderson County, KY as the project worked to get necessary financing to move the project forward. | http://content.sierraclub.org/coal/environmentallaw/plant/cash-creek-igcc http://www.courierpress.com/news/cash-creek-permit-gets-extension-ep-445105823-324946251.html
Chicago Clean Energy Project (formerly Leucadia Chicago SNG) | 2014-04-07 | Leucadia National Corp. | Chicago | Illinois | SNG | Undefined high-sulfur Illinois coal to SNG | $3 billion | D - Delayed / Cancelled | Not identified | Illinois Gov. Pat Quinn vetoed the bill that would allow the plant to begin construction. Quinn’s rejection of the bill puts the future of the plant in jeopardy because the agreement requiring companies to purchase the gas for the next 30 years was considered part of the guarantee making the plant economically viable. Following the veto announcement, Leucadia representatives stated that they would not continue to pursue development of the facility and focus efforts on other facilities around the country. | http://www.nwitimes.com/news/local/illinois/chicago/quinn-vetoes-coal-gasification-bill/article_6d4395cd-2c90-52bf-9a84-f9dfff6c2e7f.html http://articles.chicagotribune.com/2012-08-15/business/ct-biz-0815-leucadia-exit--20120815_1_coal-to-gas-plant-coal-gasification-plant-commerce-energy-council
CleanTech Energy Project | 2013-12-02 | USA Synthetic Fuel Corp. (USASF) |  | Wyoming | CTL | 30.6 mm bbls/year of synthetic crude (or 182 billion cubic feet per year) | $2.3 billion | O - Other | Not identified | This project is being developed by Cleantech Energy Company. Financing for this project has not yet been secured. The Cleantech Energy Project will be located in Wyoming and is being designed to produce 30.6 million BOE per year of pipeline quality synthetic natural gas and to capture and fully utilize the carbon dioxide produced during the synthetic natural gas manufacture. | http://www.usasfc.com/usasfc_dev/?page_id=239 http://www.nasdaq.com/markets/spos/company/usa-synthetic-fuel-corp-833509-69054
ClearFuels BTL | 2015-03-10 | ClearFuels Technology | Collinwood | Tennessee | BTL | 1,000 TPD wood material to 20 million GPY sythethic jet/diesel fuel and naptha | $200 million | O - Other | Not identified | As of March 2015, no additional information has been made available on this project. ClearFuels is 95% owned by Rentech, Inc. Original plans for this project included co-firing with coal and biomass, but has since re-defined it's feedstock as biomass only. ClearFuels and Hughes Hardwood International, Inc. (Hughes Hardwood) have executed a Memorandum of Understanding regarding the development of a commercial scale biorefinery facility for the production of renewable jet or diesel fuel. The renewable energy facility will be co-located with Hughes Hardwood’s wood component products manufacturing facility in Collinwood, Tennessee. Under the MOU, Hughes Hardwood will supply 1,000 dry ton per day of wood product for conversion to liquid fuel. As of late 2013, the facility was still considered proposed with an online date of 2014. | http://www.clearfuels.com/pdf/CF_Hughes_Hardwood_Release_2-24-10.pdf http://www.southernenvironment.org/uploads/pages/biomass_facilities_download_2013Nov01.pdf
Coffeyville Resources Nitrogen Fertilizers UAN Expansion Project | 2015-06-02 | CVR Partners | Coffeyville | Kansas | CTL | Expanding the facility’s 2,025 ton-per-day urea ammonium nitrate (UAN) production capacity to more than 3,000 tons per day. | TBD | A - Active | None - CO2 is used in production | All machinery and equipment for the project has been installed and related infrastructure is in place. Expansion project is active and producing product. | http://www.cvrpartners.com/2013-01-09_UAN_Expansion_Update_NR--F.pdf http://www.cvrpartners.com/Operations/index.html
Demonstration "Bluegas" | 2013-01-10 | GreatPoint Energy | Grand Forks | North Dakota | SNG | Biomass fuel | TBD | O - Other | Not identified | The Company currently conducts tests at a pilot plant at the University of North Dakota's Energy and Environmental Research Center which demonstrates the latest version of its technology and serves as a feedstock calibration facility for designing commercial plants. | http://www.greatpointenergy.com/developmentstatus.php
East Dubuque Plant | 2013-12-02 | Rentech Energy Midwest Corporation (REMC) | East Dubuque | Illinois | CTL, polygeneration | 1,000 tpd ammonia; 2,000 BPD clean fuels and chemicals | TBD | D - Delayed / Cancelled | Not identified | Rentech, Inc. announced plans to cease operations at, reduce staffing at, and mothball its research and development (R&D) Product Demonstration Unit (PDU), in Commerce City, CO, and to eliminate all related R&D activities. The Company's strategy is focused on more immediate growth opportunities within the energy industry that do not rely on new technologies. Project was abandoned in 2008 as it not longer fit the company's development strategy. | http://www.businesswire.com/news/home/20130228005399/en/Rentech-Close-Product-Demonstration-Unit http://phx.corporate-ir.net/phoenix.zhtml?c=66629&p=irol-newsArticle&ID=1790402&highlight=
Ely Energy Center, Phase II | 2013-12-02 | NV Energy | White Pine County | Nevada | IGCC | 1000 MW (two units) | TBD | D - Delayed / Cancelled | Not identified | No activity has been reported since 2009. Nevada SB123 has been passed by both houses in the Nevada legislature and signed into law by Governor Sandoval. By passing the bill, Nevada lawmakers have effectively eliminated coal as a fuel source for power generation. Passage of the bill is expected to cause an indefinite cancellation of the plans for the Ely Energy Center. | http://www.protectnv.org/blog/303-looking-toward-nevadas-clean-energy-future http://www.lasvegassun.com/news/2013/jun/04/nv-energy-bill-wins-passage-signaling-shift-coal/ http://www.reviewjournal.com/business/energy/nv-energy-backs-coal-fired-ely-energy-center-air-force-objects-solar-plant
Enid GTL | 2014-06-11 | Emerging Fuels Technology | Enid | Oklahoma | GTL | Undetermined | $650 million | A - Active | Not identified | Emerging Fuels Technology announced that they plan to begin engineering analysis work at the Cimarron Industrial Park in Enid, OK. The company has reserved for $6,000 a total of 67 acres at the location for 6 months with an additional 6 month option available. If work progresses, the $650 million plant would be built in 2 stages and likely employ approximately 100 people. | http://www.enidnews.com/localnews/x1535572689/Company-considering-Enid-gas-to-liquid-plant
Faustina CTC Project | 2014-08-14 | Faustina Hydrogen Products | Donaldsonville | Louisiana | CTC | 4,000 TPD ammonia; 600 TPD methanol; 450 TPD sulfur; 16,000 TPD CO2 for EOR; may also produce SNG | $1.6 billion. Financing in place according to Owner. | O - Other | CO2 to be used for EOR | Since initially being announced in 2007, little information on the project has been released. | http://www.sourcewatch.org/index.php?title=Faustina_Hydrogen_Products_Petroleum_Coke_Gasification_Project
Freedom Energy Diesel CTL | 2014-10-17 | Freedom Energy Diesel LLC | Morristown | Tennessee | GTL | Undetermined | $750 million | D - Delayed / Cancelled | Not identified | The Morristown Industrial Board has granted a one-year extension, broken into two phases---6 months (December 31, 2013) to allow Freedom Energy Diesel to obtain and present proof that it has the financing in place for the project and then another 6 months (June 30, 2014) to begin construction. This is the second extension that has been granted to the project since property for the project was provided to Freedom Energy Diesel. A clause in the property deed would transfer the land back to the City of Morristown if construction doesn't begin by the end of the current extension. Project developers have changed the direction of the plant to now use natural gas instead of coal to produce liquid fuels. The deadline to begin construction has now passed and ownership of the 115-acre site in the East Tennessee Progress Center has reverted back to the Morristown government. An option to repurchase the land has been made available should Freedom Energy Diesel secure the necessary $750 million financing. | http://lindanoe.blogspot.com/search?q=diesel http://www.citizentribune.com/?p=67136 http://www.citizentribune.com/?p=75199
Freedom Pines Biorefinery (Range Fuels BTL) | 2015-09-15 | LanzaTech | Soperton | Georgia | BTL | 320,000 bpy ethanol (10 million gpy) | TBD | A - Active | Not identified | The project appears to remain active as senior development engineer Derek Griffin is scheduled to present the keynote presentation at the International Bioenergy & Bioproducts Conference in October 2015. Site manager John Burgess announced that LanzaTech was planning to move forward with the development of the Freedom Pines Biorefinery. He stated that the company is evaluating technology left behind at the former Range Fuels site to determine if it would remain at the site or be replaced by other commercially available technology. He noted that from the time the company breaks ground it would take 20 to 24 months before operations begin. | https://www.eiseverywhere.com/ehome/110326/294092/?&&internal=1 http://www.southeastgeorgiatoday.com/index.php?option=com_content&task=view&id=10476&Itemid=117
Good Spring (aka Future Power) NGCC | 2015-09-15 | EmberClear (formerly Future Fuels LLC) / Sinopec | Schuylkill County | Pennsylvania | NGCC (initial project design was for IGCC) | 330 MW from natrual gas (initial project design was for anthracite coal; 270 MW) | $1 billion (will seek ~$610 million in US DOE loan guarantees and/or grants) | A - Active | CO2 removal is expected to be at 50% initially, nearly 100% by 2020 ("would likely be sequestered in locations interconnected by pipelines…") | EmberClear announced that it is dropping plans for a 270 MW IGCC plant and opting for a 300 MW NGCC plant instead, announcing the selection of SK E&C USA for Engineering, Procurement & Construction (“EPC”) for the 300 MW Good Spring Natural Gas Combined Cycle power plant (renamed "Good Spring NGCC"). Changed direction of plant from coal to natural gas to make use of abundant and cheap Marcellus gas supplies. EmberClear has also signed a 50:50 partnership with Tyr Energy, Inc. for ownership of the facility. Earlier in 2014 EmberClear was granted its final air quality permit from the PA DEP, moving construction of the plant one step closer. EmberClear and Tyr Energy continue to progress toward financial closing, anticipated to occur sometime in late 2015. The company expects construction on Good Spring 1 to begin in 2016 with construction of Good Spring 2 to follow at a later date. | http://www.emberclear.com/projects/good-spring-ngcc-1-2/ http://emberclearenergy.com/tag/good-spring/ http://www.garp.org/risk-news-and-resources/risk-headlines/story.aspx?newsId=71522 http://www.newswire.ca/en/story/1320765/emberclear-announces-partnership-with-tyr-energy-on-good-spring-power-projects http://republicanherald.com/news/emberclear-corp-receives-final-dep-permit-for-electricity-plants-1.1646889 http://www.marketwired.com/press-release/emberclear-announces-resumption-of-trading-and-business-plan-notes-tsx-venture-emb-1988242.htm
Green3Power WTL Plant | 2015-12-08 | Green3Power Operations Inc. | St. Lucie County | Florida | WTE | 1,000 tons/day municipal waste to an undisclosed quantity of No. 2 diesel fuel | $175 million | A - Active | Not Identified | BioPower Operations Corp. has announced that its wholly owned subsidiary Green3Power Operations Inc. (G3P) has won an award to build a $175 million renewable energy facility that will convert waste into ultra-low sulfur synthetic green No. 2 diesel fuel using G3P’s exclusively licensed gasification technology and the Fischer-Tropsch process. The facility will be built at the existing St. Lucie County Solid Waste Management Facility in Florida, and extend the life of the landfill while reducing environmentally harmful greenhouse gas emissions. | http://www.biodieselmagazine.com/articles/439207/company-to-develop-175-million-waste-to-diesel-plant-in-florida
Great Plains Urea Project | 2016-06-09 | Dakota Gasification | Beulah | North Dakota | CTC | Lignite to 1,100 tons of urea per day as well as 185,000 gallons of diesel emissions fluid per day | $500 million | A - Active | Not identified | Dakota Gasification Co. has approved the Great Plains Synfuels Plant at a cost of $402 million. The facility will produce 1,000 tons of urea daily, have the capacity to store 53,000 tons on site, and have the ability to load up to 110 railcars. The plant will also produce diesel emission fluid which will be stored in a 1.1 million gallon tank. The plant is expected to be operational sometime in 2017. In June 2014, IHI E&C international Corporation was awarded a contract to provide detailed engineering and procurement services for the Great Plains Synfuels Plant. As of February 2015, more than 50 percent of the engineering was complete and 25 percent of major equipment has been purchased. As of June 2015, the company anticipates engineering work to be complete by the end of 2015 and is anticipating the arrival of several major pieces of equipment in November 2015. The company also increased the budget for the facility to $500 million following higher than anticipated construction bids. A December 2015 YouTube video shows the arrival of the pool reactor, high pressure stripper, and high pressure scrubber, the main components of the plant. These elements were developed by Stamicarbon. In April 2016, onsite construction contractor RUST Constructors set in place the pool reactor, one of the last remaining major components to be set in place at the facility. Dakota Gasification anticipates a second quarter 2017 opeartional startup. | http://www.prairiebizmag.com/event/article/id/17626/ http://www.dakotagas.com/News_Center/Publications/Feature_Articles/approved-dakota-gas-project-adds-to-product-diversity.html http://www.ihi-ec.com/ihi-ec-international-corporation-awarded-ep-services-contract-for-urea-project/ http://www.basinelectric.com/News-Center/News-Articles/News-Briefs/engineering-for-dakota-gasification-companys-urea-project-reaches-halfway-mark.html http://www.dakotagas.com/News_Center/Publications/News_Briefs/progress-continues-on-urea-project.html https://www.youtube.com/watch?v=37uigOKO1fI https://www.basinelectric.com/News-Center/News-Articles/News-Briefs/major-equipment-set-in-place-at-dakota-gasification-companys-urea-project.html
HECA: Hydrogen Energy California Project (formerly Carson Hydrogen Power Project) | 2015-09-15 | SCS Energy California LLC (formerly: Hydrogen Energy International LLC (HEI) [JV: BP and Rio Tinto]) | Kern County | California | IGCC/H2/polygeneration | 25% petcoke / 75% coal mix producing 180 MMSCFD H2, used to generate 300 MW, 2208 tpd of urea, and undefined amount of liquid sulfur. | $3.9 billion | D - Delayed / Cancelled | 87% CO2 capture will be used for EOR, while 13% will be used to produce urea | In July 2015, the California Energy Commission (CEC) agreed to suspend the HECA project for 6 months at the request of the developer so as to allow the company to find a buyer of the CO2 that will be produced. Opponents to the plant had hoped the project would be terminated completely. In providing the suspension, the CEC outlined several milestones that will need to be meet else the project will be terminated. In May 2015, the CEC chose not to decide on a request to suspend its review of the HECA power plant. HECA had asked the CEC to suspend the project for six months to allow for a CO2 buyer to be found. The CEC also did not act on a motion by HECA opponents to end the project completely. In March 2015, environmental groups have petitioned the CEC to terminate the HECA project. The groups cited significant emissions that would be produced from the transport of fuel supply to the plant as one reason for stopping the proposed plant. The project had been at a standstill for almost six months as project oficials had not submitted necessary paperwork to allow the project to move forward. One key part of the delayed paperwork wsa an agreement for CO2 supply with the Elk Hills oil field operator. The San Joaquin Valley Air Pollution Control District issued the final determination of compliance (FDOC) for air pollution, after addressing public comments. The decision by the Air District means HECA has provided sufficient information and mitigation proposals showing that it can operate in full compliance with all air pollution rules and regulations. The facility may face additional hurdles as a lawsuit against the coal handling facility that will supply the HECA plant has been filed in Kern County Superior Court. The lawsuit was filed contending that the coal handling facility is in violation of the California Environmental Quality Act for inappropriately waiving an extensive environmental review prior to increasing mazimum handling volumes from 900,000 tons to 1.5 million. | http://www.naturalgasintel.com/articles/102950-california-suspends-syngas-carbon-capture-project-for-six-months http://www.bakersfieldcalifornian.com/business/kern-gusher/x406539143/Groups-ask-state-to-shelve-coal-project http://www.fierceenergy.com/story/hydrogen-energy-california-coal-plant-under-fire/2015-03-03 http://www.energy.ca.gov/sitingcases/hydrogen_energy/documents/others/2013-07-08_San_Joaquin_Valley_Air_Pollution_Control_District_Notice_of_Final_Determination_of_Compliance_TN-71610.pdf http://hydrogenenergycalifornia.com/wp-content/uploads/file_attachments/311020122134460/WebENGHECAFallNewsletter9032013.pdf http://www.bakersfieldcalifornian.com/local/x62929100/Lawsuit-over-coal-depot-could-affect-HECA-project http://www.kerngoldenempire.com/story/d/story/no-decision-on-request-to-suspend-review-of-power/11457/84rUp561UEGCmVYxQsmLPQ
Homeland Fuels Illinois CTL | 2015-06-04 | Homeland Fuels Company | Springfield | Illinois | CTL | 150 tpd Illinois coal to 1,000 bbl/d diesel. | TBD | A - Active | Not identified | Homeland Fuels intends to develop a CTL project, focusing on diesel production. The facility will convert 150 tpd Illinois coal to 1,000 bbl/d diesel fuel. The facility will be considered a stepping stone towards a 2,000 to 3,000 tpd CTL plant. Johnson Matthey Davy Technologies' Fischer Tropsch technology has been chosen to be used at the facility. | http://www.gasification.org//uploads/eventLibrary/2014_3.2_Jacobs_Dieter_Lamprecht.pdf http://www.downstreambusiness.com/item/Homeland-Fuels-Tap-JM-Davys-Can-FT-Technology_138934
Hyperion Energy Center aka "Gorilla Project" | 2013-12-02 | Hyperion Refining, LLC | Union County | South Dakota | IGCC/H2, polygeneration | 7,400 TPD petcoke to 450 million SCFD H2; 200 MW and 2.4 mmlb/hr steam. [507 MW total IGCC capacity to be used onsite] | $10 billion | D - Delayed / Cancelled | Not identified; 90+% carbon-capture capable; studies ongoing to locate suitable CO2 sequestration projects in the vicinity; either EOR or saline aquifer sequestration | As part of Hyperion Refining’s reevaluation of the Hyperion Energy Center, the Company will consider filing a new application for its air permit rather than renewing the existing consent. The company has relinquished rights to all land it had acquired for the project. | http://denr.sd.gov/Hyperion/Air/20130315PressRelease.pdf http://www.ktiv.com/story/22200219/2013/05/08/hyperion-energy-lets-go-of-all-land-in-union-county-sd http://siouxcityjournal.com/business/local/another-roadblock-for-billion-union-county-s-d-oil-refinery/article_1178828e-a16f-5563-98fb-cf347d75c5ab.html
ICM/JUM Gasification Demonstration | 2015-12-15 | ICM Inc., JUM Global LLC | San Jose/Santa Clara | California | BTG | 10 tpd of waste biomass and wastewater facility biosolids to high quality syngas | TBD | A - Active | Not identified | ICM Inc. announced a signed contract with JUM Global LLC, a global waste solution developer contracted with the City of San José, California, for a gasification demonstration unit using ICM’s proprietary technology. This gasification demonstration unit will be operated at the San José-Santa Clara Regional Wastewater Facility, which will process up to 10 short tons per day of urban waste biomass from the San José solid waste collection program, such as urban woody biomass, storm debris, yard waste, tree trimmings, as well as construction and demolition materials, blended with a small portion of biosolids from the wastewater facility. The gasification unit will help the region by demonstrating a process, which can be utilized in both the disposition and the application of these materials to produce a high quality syngas (i.e., producer gas), which can ultimately and efficiently be used to produce transportation fuels. | http://www.biomassmagazine.com/articles/11649/icm-jum-global-sign-contract-for-advanced-gasification-project http://waste-management-world.com/a/10-tpd-gasification-technology-demonstration-unit-to-roll-out-in-san-jos-california
Illinois Clean Fuels Project | 2014-06-13 | American Clean Coal Fuels | Coles County | Illinois | CTL | 4.3 million TPY coal/biomass to 400 million GPY diesel and jet fuel | $3.6 billion | D - Delayed / Cancelled | Capture with underground sequestration; sequestration required by regulations | Activity last reported on 3/8/2009 but the project appears to be active. Construction schedule was delayed to 2010-2013. Last known activity is approved financing for permitting and engineering work. The lack of announced activity/progress on the project suggests that the project has been abandoned. | http://www.cleancoalfuels.com/blog/
Indiana - Rockport SNG | 2015-03-10 | Indiana Gasification, LLC, subsidiary of Leucadia National Corp. | Rockport | Indiana | SNG | 3.85 million TPY coal to 47 million mmBtu per year of SNG, 134 MW electricity, and an undefined amount of sulfuric acid | $3.65 billion | D - Delayed / Cancelled | Plant is able to capture 90%; will be sold for use in EOR. | In March 2015, the Indiana Department of Enrivonmental Management notified Indiana Gasification LLC they had revoked the necessary air permit for the facility at the request of Leucadia National Corp. The request for revocation was made as construction on the plant had never begun. Lawmakers have approved tough new regulatory oversight of the proposed $2.8 billion Rockport coal-to-gas plant. The Indiana Supreme Court has upheld the Indiana Finance Authority’s 30-year contract to buy 80 percent of the synthetic natural gas made at the plant financed by Leucadia National Corp. at a pre-negotiated rate, and then resell that product on the open market. The court did acknowledge that a slight change of wording in the contract was not significant enough to void the contract. Had the court found the wording change significant, another review by utility regulators would have been necessary, which in turn would subject the project to new regulatory standards that were not in place when the project was initially approved. The court's decision now places the decision on whether to continue with the project into the hands of the developer and the Indiana Finance Authority. | http://wlfi.com/2015/03/09/indiana-regulators-revoke-coal-gasification-plants-permit/ http://www.tristatehomepage.com/story/indiana-supreme-court-rules-in-favor-of-rockport-p/d/story/L907kHKtmUSaxFd08X8pvw
Kemper County IGCC Project (Plant Ratcliffe) | 2016-06-09 | Mississippi Power (Southern Co.) | Kemper County | Mississippi | IGCC | 582 MW | $6.6 billion | A - Active | 65% capture (to be eligible for additional tax credits/grants, etc.) for EOR Removal of: over 99% SO2 & P25, at least 90% Hg (another source: 92% mercury), NOX emissions of less than 0.07 lb/million Btu. | The latest financial filings related to the Kemper County project show the cost rising yet again, this time by an additional $18 million, taking the total cost to just short of $6.7 billion and the completion date has now been pushed to late September 2016. According to a February 2016 filing by Mississippi Power, the proposed plant's coal gasifiers are now anticipated to being operation by the end of August 2016. Increasing costs have now pushed the total project cost to more than $6.6 billion, nearly triple the originally budgeted costs for the facility. In August 2015, an emergency rate increase was approved by state regulators to keep the owner of the plant, Mississippi Power, financial afloat. The 18% rate increase is intended to be temporary but may become permanent. In May 2015, South Mississippi Electric (SME), an electric cooperative that has been Mississippi Power Co.’s (MPC’s) long-time backer in the development of the Kemper energy facility, has pulled out of the project, citing delays in project schedule and increased participation costs as reasons for its withdrawal. In March 2015, a major milestone was reached in the Kemper project as the plant's gasifiers were fired for the first time, operating as planned. With the intitial firing of the gasifiers, plant operators now look towards another milestone they hope to achieve later in the year - production of syngas from lignite coal. It was not all good news for Kemper as another $45 million will be required to see the plant to completion, the third increase to the total cost in the past several months. Southern company announced that the proposed Kemper IGCC Project would now be delayed until March 2016 and would cost an additional $496 million dollars, bringing the total cost of the project to just over $6.1 billion. This increase follows an earlier announcement of $59 million that pushed completion to June 2015. The newly announced additional costs are needed for material and labor during plant startup as well as interest on already invested funding. The plants turbines were brought online in August, fueled by natural gas that is piped to the plant. Since the plant was approved for construction, the cost has more than doubled from an original estimate of $2.8 billion. The original timeframe would have brought the completed plant online in 2013. | http://www.greentechmedia.com/articles/read/southern-company-is-raising-rates-18-to-pay-for-its-carbon-capture-plant http://www.hattiesburgamerican.com/story/news/2015/03/09/kemper-plant-first-fire/24657321/ http://www.pennenergy.com/articles/pennenergy/2015/02/power-news-kemper-overruns-climb-another-45mm.html http://www.mississippipower.com/about-energy/plants/kemper-county-energy-facility/facts http://www.pennenergy.com/articles/pennenergy/2014/10/coal-news-costs-rise-by-another-496mm-at-kemper-plant.html http://www.pennenergy.com/articles/pennenergy/2014/10/coal-news-again-costs-rise-and-completion-delayed-at-kemper.html http://www.powermag.com/kemper-project-loses-key-power-buyer-due-to-delays-high-costs/ http://www.powermag.com/kemper-igcc-in-service-date-pushed-to-q3-costs-surge-again/ http://www.bizjournals.com/atlanta/morning_call/2016/04/price-of-southern-co-plant-rises-to-6-7-billion.html
Kentucky NewGas SNG | 2014-08-14 | Peabody Energy, ConocoPhillips | Muhlenberg County | Kentucky | SNG | Coal and petcoke 3.5 million TPY to SNG 60-70 BCF/Y | $3 billion | D - Delayed / Cancelled | Less than 5% of the emissions of a traditional coal-fired power plant. Over 99% of sulfur will be recovered and sold | Project has been officially cancelled as the project developer, Peabody Energy, notified the Commonwealth of Kentucky in 2013 that no additional development work would occur. | http://www.globalccsinstitute.com/project/kentucky-newgasucky
Lake Charles Clean Energy | 2014-10-10 | Leucadia National | Port of Lake Charles, Calcasieu Parish | Louisiana | SNG, polygeneration | 7.4k TPD petcoke to 120 MMSCF per day SNG and 2k TPD sulfuric acid | $2.5 billion | D - Delayed / Cancelled | 85% CO2 capture for used in EOR. More than 4 million tons of CO2 emissions, transported as compressed CO2 through 12-mi Denbury pipeline for EOR in Hastings and Oyster Bayou oilfields. CCS project via NETL's Clean Coal Power Initiative (CCPI) | In October 2014, Leucadia National Corporation announced that development on the Lake Charles Clean Energy facility would cease. Development on the project was ceased after the company came to the conclusion that the final cost of the facility would be higher than anticipated. Prior to ceasing work, more then $20 million had been invested in the region on such things as lease payments and property improvements. | http://www.sulphurdailynews.com/article/20141007/NEWS/141009743/1994/NEWS
Lake County Waste-to-Ethanol | 2013-12-04 | Powers Energy 1 | Lake County | Indiana | WTEth | 2k-10k TPD MSW to 30-150 million GPY ethanol (other source says up to 175 million GPY) | $285 million | D - Delayed / Cancelled | Not identified | Lake County Solid Waste Management District Board, in a unanimous vote, canceled its contract with Powers Energy for the development of a waste-to-ethanol plant. The board cited Powers Energy's repeated inability to secure financing as well as providing viability of the planned process as its reason for ending the project. The project was initially approved in 2008 but never got off the ground. | http://www.nwitimes.com/news/local/lake/lake-county-officials-cancel-trash-to-ethanol-contract/article_e98e7ea1-641b-5018-a60e-5a77b8a3c331.html
Lebanon WTE Gasification Project | 2016-06-09 | PHG Energy | Lebanon | Tennessee | WTE | 64 tons per day of waste wood, scrap tires, and sewer sludge to 300 kW electricity | $3.5 million | A - Active | Not identified | Nashville, Tennessee based waste to energy firm, PHG Energy and the city of Lebanon, Tennessee, have signed a contract to develop a downdraft gasification plant that will cleanly convert up to 64 tons (58 tonnes) per day of blended waste wood, scrap tyres and sewer sludge. The waste to energy plant, which is expected to enter service in early 2016 will generate up to 300 kW of electricity. Groundbreaking for the facility took place in November 2015. | http://waste-management-world.com/a/waste-to-energy-firm-phge-to-build-64-tpd-downdraft-waste-gasification-plant-in-lebanon-tennessee http://www.phgenergy.com/case-study/lebanon-tenn
Lima Energy Project | 2016-03-01 | American Future Fuels Corp. | Lima | Ohio | IGCC/SNG/H2, polygeneration | Three Phases: 1) 2.7 million barrels of oil equivalent (boe), 2) expand to 5.3 million boe (3) expand to 8.0 million boe (47 billion cf/y), 516 MW | $2 billion | A - Active | Unspecified amount captured and used for EOR in eastern Ohio oilfields (partnership with HTC PurEnergy) | The Ohio EPA has approved the final air permit for the Lima Energy facility. The company is presently working on the engineering and financing portions of the project and expect to have the facility operational within two years of construction start. On 10/1/13, Lima Energy Company announced that they had agreed to supply the nearby Husky Energy Lima Refinery with upwards of 80 million barrels of Global 1 Ultra Clean Synthetic Crude. Global 1 is the product that will be produced at the Lima Energy Project. As of late 2013, the site of the proposed project had been cleared, removing all remaining structures from the former Lima Locomotive Works. Permit applications have been submitted to the Ohio EPA, which is in the process of debating whether to approve. The developer of the project has changed following the bankruptcy filing of original developer USA Synthetic Fuel Corporation. The project has been taken over by American Future Fuels Corp. The project is anticipated to be the same as it was under USASFC but will require the transfer of permits and other legal changes before any work can commence. | http://www.hometownstations.com/story/25592798/ohio-epa-approves-lima-energy-permits http://www.usasfc.com/usasfc_dev/?page_id=237 http://www.limaohio.com/news/news/860475/Community-largely-supportive-of-Lima-Energy-project http://limaohio.com/news/149379/lima-energy-applied-for-certificate-with-plans-to-transfer-it
Many Stars CTL | 2014-10-17 | Australian-American Energy Co. (Terra Nova Minerals or Great Western Energy), Crow Nation | Big Horn County | Montana | CTL | First phase: 8,000 BPD liquids | $1 billion | O - Other | 95% CO2 capture for either saline aquifer sequestration or sold for EOR use | No new information on the project has been released and the project's website in relation to news about the project was last updated in 2011. While Crow Tribal Leaders negotiate PRB coal contracts with Cloud Peak Energy for shipping overseas, they announced that plans for the CTL Plant are still seeking financing and do not consider the project to be cancelled. | http://news.yahoo.com/mont-tribe-signs-coal-deal-192548021.html
Medicine Bow Fuel and Power Project | 2016-06-09 | DKRW Advanced Fuels | Carbon County | Wyoming | CTL | 3 million TPY coal to 11,700 BPD of gasoline | $1.75 billion | D - Delayed / Cancelled | CO2 to be sold for EOR in Wyoming or geologically sequestered. | According to a January 2016 news article, DKRW's permint from the Wyoming Industrial Siting Council will expire if a construction schedule and other filings are not provided by June 18, 2016. DKRW, while not abandoning the project, believes they will be unable to meet the requirement. In June 2015, DKRW Advanced Fuels announced that they are considering downsizing their proposed CTL plant in light of the recent drop in oil prices. The company would be required to amend their construction permit but would not have to submit a new application. In February 2015, the Wyoming state legislature included approximately $10 million for upgrades to roads and bridges that would be used to access the site for facility construction. The money would be made available so long as project developer, DKRW, is able to securing financing and a construction contractor. On September 20, 2013, DKRW Advanced Fuels submitted a request to delay construction for up to 30 months to address concerns about scheduling and project impacts. The Wyoming Industrial Siting Council approved a 39-month extension for the project in December 2013. In March 2014, DKRW ended its relationship with Sinopec Engineering Group, the projects contractor. In April 2014, Arch Coal, one of the projects investors and supplier of coal to the project, announced in a statement to investors that they see the project as a total loss on the company's investment of $25 million. It is unknown if Arch will still supply the project with coal. DKRW continues to discuss with DOE a loan guarantee worth $1.75 billion, with a focus on whether DKRW can secure a new construction firm. | http://billingsgazette.com/news/state-and-regional/wyoming/wyoming-plans-for-dkrw-coal-to-liquid-plant-stall/article_61679478-7b3e-5ac1-aaf1-a2fa0fd83cc4.html http://trib.com/business/energy/dkrw-considers-downsizing-proposed-coal-gasification-plant-residents-doubtful/article_ad0e1f5f-08bb-5b92-964f-d86f68266e48.html http://trib.com/business/energy/still-waiting-wyoming-budget-calls-for-m-for-dkrw-infrastructure/article_d9a300f6-1ce9-55a6-9bee-2cb93824f3d2.html http://wyomingpublicmedia.org/post/dkrw-asks-another-construction-delay-its-coal-liquids-facility http://www.therepublic.com/w/WY--Coal-To-Liquids-Plant http://wyomingpublicmedia.org/post/arch-coal-writes-investment-dkrw-coal-gas-project http://www.thefreelibrary.com/United+States+%3A+DKRW+ADVANCED+FUELS+continues+talks+with+DOE+over...-a0374708070 http://www.washingtontimes.com/news/2016/jan/7/plans-for-dkrw-coal-to-liquid-plant-stall/?utm_source=RSS_Feed&utm_medium=RSS
Mesaba Excelsior Energy Coal Gasification Project I | 2013-02-12 | Excelsior Energy, Xcel Energy | Taconite | Minnesota | IGCC | 603 MW | $2.0 billion | D - Delayed / Cancelled | Not identified | Excelsior Energy sought to convert its permits from coal gasification to conventional natural gas plant permits for both Project 1 and Project 2 | http://www.sourcewatch.org/index.php?title=Mesaba_Energy_Project
Mesaba Excelsior Energy Coal Gasification Project II | 2013-02-12 | Excelsior Energy, Xcel Energy | Itasca County | Minnesota | IGCC | 603 MW | TBD | D - Delayed / Cancelled | Not identified | Excelsior Energy sought to convert its permits from coal gasification to conventional natural gas plant permits for both Project 1 and Project 2 | http://www.sourcewatch.org/index.php?title=Mesaba_Energy_Project
Moss Point (formerly Moss Point SNG) | 2013-07-09 | Mississippi Clean Energy (formerly Mississippi Gasification) (a subsidiary of Leucadia National Corp.) | Jackson County | Mississippi | PTL | 7000 tons per day of petcoke (from Chevron refinery & Koch Industries) to undefined amount of gasoline, methanol or both. Also: 500,000 TPY sulfuric acid | $2.2 billion | D - Delayed / Cancelled | 90% CO2 capture (4 million TPY). DOE Loan Guarantee Program from ARRA, with Denbury: $840,000 to demonstrate capture and sequestration of CO2. | Mississippi Clean Energy, formerly Mississippi Gasification (a subsidiary of Leucadia National Corp.) reported to the Jackson County, Mississippi Economic Development Foundation that the company would be unable to extend the current lease option for the land/facility which would become the Moss Point gasification plant. The site is being considered for other projects, while Mississippi Clean Energy and Leucadia National Corp. reported that they will continue to pursue the project at a different location. | http://blog.gulflive.com/mississippi-press-business/2013/07/mississippi_gasification_wont.html
NABFG Weirton CTL | 2013-06-07 | North American Biofuels Group | Weirton | West Virginia | CTL | Undetermined | $400 million | O - Other | Not identified | No activity on ownership's part since August 2011; however, no acknowledgement of project being cancelled either. | http://gas.carboncapturereport.org/cgi-bin//profiler?key=american_bio_fuels_group&pt=3
Pallas Formed Fuels (formerly Ohio River Clean Fuels, formerly Baard Generation 1 & 2) | 2015-03-10 | Planck Trading Solutions LLC | Wellsville | Ohio | GTL | 500 MMcf/d natural gas to 250 MW and 53,000 BPD ultra-clean diesel, jet fuel, and naptha | $6 billion | O - Other | "Will capture and ultimately sequester at least 85%" of CO2 | In March 2015, representatives of the Ohio Development Services Agency announced that they were sufficiently satisfied in regards to development at the project site such that the Columbiana County Port Authority would not be required to repay $148,000 grant it was initially awarded when Baard Energy initially proposed its CTL plant. Also in the announcement it was stated that Planck Trading Solutions had acquired all 510 acres of land that were initially to be purchased by Baard. Under Planck ownership, the project is now known as Pallas Formed Fuels. Most recent reports reference uncertainty regarding air quality permits and challenges to the air quality permits that have been issued. The company has not issued reports countering challenges or stating progress on the project. Planck Trading was initially brought in to help Baard with financing for the project and eventually took over controlling interest from Baard, at which time Planck changed the direction of the project from CTL to GTL. | http://www.morningjournalnews.com/page/content.detail/id/560223/Route-30--fuel-plant-projects-may-be-off-the-radar-but-still-showing-some-blips-of-life.html?nav=5006 http://www.ohioenvironmentallawblog.com/tags/nsr/ http://www.naturalgasintel.com/articles/print/87985-long-delayed-ohio-liquefaction-plant-gets-new-life http://businessjournaldaily.com/drilling-down/columbiana-port-authority-signs-chesapeake-2012-3-20
Pinto/Velocys Ashtabula GTL | 2016-06-09 | Ashtabula Energy, a division of Velocys (formerly Pinto Energy) | Ashtabula | Ohio | GTL | 4,200 bpd with future expansion possibility to 10,000 bpd. | $200 million | A - Active | Not identified | The Ohio EPA has issued the required air permits for the project under its original scope but these may need to be revised based on intended changes Velocys has for the proejct. Wastewater discharge permits were approved and issued in July 2015. Water permit applications were submitted to the Ohio EPA in January 2015 but no additional information has been provided on whether those have also been granted. Velocys is seeking to build the GTL refinery on an 80-acre site in Ashtabula Township and has expanded the size of the facility to 4,200 barrels per day. The project was previously proposed by Pinto Energy, which Velocys acquired in June 2013. As its first facility, Pinto Energy was developing an approximately 2,800 barrels per day plant at an industrial site that it owns near the Port of Ashtabula, Ohio. The project will have access to abundant low-cost natural gas from the Marcellus shale region, as well as benefitting from substantial existing infrastructure. Initial engineering for the facility is complete and the air permit has been issued. Final investment decision is expected within six to nine months. Future expansions could see installed capacity of 10,000 bpd or more at the site. | http://wkbn.com/2015/01/17/firm-seeks-to-open-200-million-refinery-plant-in-ne-ohio/ http://www.velocys.com/financial/nr/nr140625.php http://www.velocys.com/press/pdf/Downstream_Business_Velocys_Hopes_To_Start_Ohio_GTL-Plant_Construction_In_2015.pdf http://www.naturalgasintel.com/articles/102997-planned-ohio-gtl-facility-receives-key-permit
Primus BTL | 2016-06-09 | Primus Green Energy | Hillsborough | New Jersey | GTL | Commercial demonstration plant on scale to a 2,000 bpd facility. | TBD | A - Active | Not identified | Primus Green Energy Ltd.is presently operating a commercial demonstration plant at its facility in Hillsborough, NJ. The plant has logged over 8,000 hours of operation converting natural gas to gasoline and methanol. The company has plans for direct biomass to gasoline conversion. The company's website states that they are currently executing several commercial projects in North America and around the world but does not provide any specific details. | http://www.primusge.com/operations/commercial-demonstration-plant/ http://www.primusge.com/operations/commercial-projects/
Red Rock Biofuels | 2016-03-01 | Joule | Lakeview | Oregon | BTL | 140,000 tons of biomass feedstock to 15 million gal/yr of jet fuel, diesel, and naphtha. | $200 million | A - Active | Not identified | In January 2016, Joule completed the acquisition of Red Rock Biofuels as part of Joule's attempt to accelerate commercialization of ultra-low carbon fuels. Joule intends to integrate Red Rock's scaled down version of Fischer Tropsch with their own Helioculture technology. In July 2015, Red Rock Biofuels announced that they have a contract in place for FedEx to purchase 3 million gallons of jet biofuel a year from the company's to be built biorefinery in Lakeview, OR. In March 2015, Red Rock Biofuels LLC announced a partnership with Flagship Ventures, with Flagship providing financial and strategic expertise as the project progresses. Flagship will also serve as an advisor for future fundraising efforts. Red Rock Biofuels LLC is in the process of developing several biomass refineries using gasification technology to produce liquid fuels including jet fuel, diesel, and naphtha. The company already has a supply contract with Southwest Airlines for the purchase of 3 million gallons annually. The company has also received a $70 million federal grant to help build refinery in Oregon. Groundbreaking is expected in the summer of 2015 with the facility going into operation sometime in 2017. | http://www.denverpost.com/business/ci_28513304/red-rock-biofuels-power-fedex-jets-under-new http://www.businesswire.com/news/home/20150317005218/en/Investment-Flagship-Ventures-Brings-Red-Rock-Biofuels#.VQl0Ko7F90a http://www.redrockbio.com/Technology.html http://www.bizjournals.com/denver/blog/earth_to_power/2014/09/red-rock-biofuels-lands-contracts-with-southwest.html http://biomassmagazine.com/articles/12817/joule-completes-acquisition-of-red-rock-biofuels
REG Geismar, LLC (formerly Dynamic Fuels Bio-Synfining BTL) | 2014-10-17 | Renewable Energy Group, Inc. | Geismar | Louisiana | BTL | 284,500 TPY of animal byproduct fat/grease to 75 mil. GPY liquid fuels | $158 million | A - Active | Not identified | Plant constuction is complete and facility is in operation. In June 2014, ownership of the facility transferred to Renewable Energy Group, Inc. and its subsidiary REG Synthetic Fuels, LLC upon closing of acquisition deals with both Tyson Foods, Inc. and Syntroleum Corporation. | http://regi.com/node/686
Rentech Energy Midwest Facility | 2013-04-05 | Rentech Energy Midwest Corporation (REMC) | East Dubuque | Illinois | CTL | 1,250 bbl/day diesel | TBD | D - Delayed / Cancelled | Not identified | Rentech, Inc. announced plans to cease operations at, reduce staffing at, and mothball its research and development (R&D) Product Demonstration Unit (PDU), in Commerce City, CO, and to eliminate all related R&D activities. The Company's strategy is focused on more immediate growth opportunities within the energy industry that do not rely on new technologies. | http://phx.corporate-ir.net/phoenix.zhtml?c=66629&p=irol-newsArticle&ID=1790402&highlight=
Rentech/Peabody Joint Development Agreement (JDA) | 2013-04-05 | Rentech/Peabody Coal | undefined | Kentucky | CTL | 10,000 and 30,000 BPD | TBD | D - Delayed / Cancelled | Not identified; plant seeking long term CO2 offtake agreements | Rentech, Inc. announced plans to cease operations at, reduce staffing at, and mothball its research and development (R&D) Product Demonstration Unit (PDU), in Commerce City, CO, and to eliminate all related R&D activities. The Company's strategy is focused on more immediate growth opportunities within the energy industry that do not rely on new technologies. | http://phx.corporate-ir.net/phoenix.zhtml?c=66629&p=irol-newsArticle&ID=1790402&highlight=
Rentech/Peabody Minemouth | 2013-04-05 | Rentech/Peabody Coal | undefined | Montana | CTL | 10,000 and 30,000 BPD | TBD | D - Delayed / Cancelled | Seeking either underground sequestration sites or CO2 for EOR offtake agreements (what they refer to as "CO2 solutions") | Rentech, Inc. announced plans to cease operations at, reduce staffing at, and mothball its research and development (R&D) Product Demonstration Unit (PDU), in Commerce City, CO, and to eliminate all related R&D activities. The Company's strategy is focused on more immediate growth opportunities within the energy industry that do not rely on new technologies. | http://phx.corporate-ir.net/phoenix.zhtml?c=66629&p=irol-newsArticle&ID=1790402&highlight=
Rialto Project | 2013-04-05 | Rentech | Rialto | California | BTL | 1,000 dry tons/d feed 9 million gallons per year, 35MW | $430 million | D - Delayed / Cancelled | Not identified | Rentech, Inc. announced plans to cease operations at, reduce staffing at, and mothball its research and development (R&D) Product Demonstration Unit (PDU), in Commerce City, CO, and to eliminate all related R&D activities. The Company's strategy is focused on more immediate growth opportunities within the energy industry that do not rely on new technologies. | http://phx.corporate-ir.net/phoenix.zhtml?c=66629&p=irol-newsArticle&ID=1790402&highlight=
Secure Energy CTL (aka MidAmericaC2L) | 2015-12-15 | MidAmericaC2L /Siemens | McCracken County | Kentucky | CTL | 10,200 bpd gasoline | $1.3 Billion | O - Other | Not identified | Per a 2015 Siemens presentation at 7th International Freiberg/Inner Mongolia Conference, the company listed the MidAmerica C2L project as one of several that planned to make use of Siemens' gasification technology. The MidAmerica C2L Gasification Plant remains an active project but no significant project development updates have been released as of July 2011. | http://tu-freiberg.de/sites/default/files/media/professur-fuer-energieverfahrenstechnik-und-thermische-rueckstandsbehandlung-16460/publikationen/2015_07-1.pdf http://www.sierraclub.org/environmentallaw/coal/getBlurb.aspx?case=ky-secure-energy-paducah-gasification-plant.aspx
Sierra BioFuels Plant | 2016-06-09 | Fulcrum Bioenergy | McCarran, Storey County | Nevada | WTL | 200,000 tons/yr MSW to 10 million gallons/yr of SPK jet fuel or diesel | $266 million | A - Active | Not identified | Fulcrum Energy has completed permitting, front-end engineering and site preparation activities for their first MSW to fuels plant, the Sierra BioFuels Plant, located in the Tahoe-Reno Industrial Center, in the City of McCarran, Storey County, Nevada. The Sierra BioFuels Plant will be comprised of a Feestock Processing Facility and a Biorefinery that will convert approximately 200,000 tons of prepared MSW feedstock into more than 10 million gallons of SPK jet fuel or diesel annually. Fulcrum has entered into long-term, zero-cost MSW feedstock agreements with Waste Management and Waste Connections, two of the largest waste service companies in North America, and a fuel off-take agreement with Tenaska BioFuels. The Sierra BioFuels Plant is expected to be one of the United States’ first fully operational, commercial-scale MSW-to-renewable fuels production plants. The plant is expected to begin commercial operation in 2017. In September 2014, Fulcrum received a $105 million loan guarantee from the USDA as part of the Biorefinery Assistance Program. In May 2015, Fulcrum awarded an engineering, procurement, and construction contract to Abengoa. In June 2015, United Airlines announced that they had invested $30 million in Fulcrum BioEnergy, for which they receivedan option to invest in five future commercial-scale aviation biofuels plants, as well as an offtake agreement for up to 90 million gallons of biofuels annually. The new plants could likely begin construction between 2015 and 2022. | http://www.fulcrum-bioenergy.com/facilities.html http://biomassmagazine.com/articles/10889/usda-awards-loan-guarantee-to-fulcrum-sierra-biofuels http://www.biofuelsdigest.com/bdigest/2015/06/30/united-airlines-invests-30m-in-fulcrum-bioenergy-inks-1-5b-in-aviation-biofuels-contracts/
Southern California Edison Utah IGCC | 2014-06-13 | Southern California Edison | Emery County | Utah | IGCC | 1 million TPY Coal to 500 MW | TBD | D - Delayed / Cancelled | 90% capture and sequestration in underground saline aquifer, 20-mi. east of plant with ~500 million ton capacity | The project failed to obtain DOE funding and developer Southern California Edison attempted to partially fund the project through rate increases but those increases were denied by the California Public Utilities Commission. | http://content.sierraclub.org/coal/environmentallaw/plant/green-river
Southern Illinois Coal-to-SNG Project | 2014-06-13 | Power Holdings of Illinois, LLC | Jefferson County | Illinois | SNG | 5 million TPY Illinois bituminous coal to 65 BCFY SNG | $2.2 billion - $2.3 billion | D - Delayed / Cancelled | Capture 50% (possibly 90%) CO2 for EOR | Illinois' environmental agency has denied a permit request to build a $2 billion plant to convert coal to synthetic natural gas in southern Illinois, further clouding prospects for the clean-energy project already more than six years in the making. According to company announcement, the project is presently dead due to low natural gas prices and a lack of buyers for the produced SNG. | http://finance.yahoo.com/news/illinois-epa-rejects-coal-gas-projects-permit-172519394--finance.html http://articles.chicagotribune.com/2012-05-25/business/ct-biz-0525-coal-plants--20120525_1_million-british-thermal-units-natural-gas-gasification
Sundrop Fuels BTL/GTL | 2016-03-01 | Sundrop Biofuels | Alexandria, Rapides Parish | Louisiana | BTL/GTL | About 300,000 - 400,000 TPY forest waste and an undefined amount of hydrogen to 1.6 mm bpy (50 million GPY) gasoline. | $450 to $500 million | A - Active | Not identified | In December 2015, Sundrop Fuels began commissioning and operation of their Integrated Bioreforming Demonstration Facility at their Longmont, CO headquarters. In March 2015, Sundrop Fuels received approval for its Part 1 application to the US DOE Loan Guarnatee Program. These funds would be used to finance its commercial plant in Alexandria, Louisiana. Earlier in the year, the company expanded its R&D facility in Longmont, Colorado to include a fully integrated pilot plant system. In July 2013, Sundrop announced that it had selected IHI E&C International Corp. as contractor for its combined commercial and demonstration plant. The plant will have the capability of producing 60 million gallons of gasoline from natural gas while providing Sundrop a facility to prove its proprietary biomass to gasoline gasification technology. Earlier in the year the company purchased nearly 1,200 acres of land near Alexandria, LA in Rapides Parrish. | http://www.sundropfuels.com/About%20Us/about http://www.sundropfuels.com/assets/white_papers/33.pdf http://www.sundropfuels.com/assets/white_papers/22.pdf
Sweeny Refinery Gasification Project | 2013-03-25 | ConocoPhillips | Sweeny | Texas | IGCC | 5,000 TPD petcoke to 400 MW (one source says 683 MW, may be output equivalent) elec., also H2 (~65 MMCFD) | $2 billion | D - Delayed / Cancelled | ~85% of CO2 from process stream will be captured, over 5 million tons sequestered into depleted oil or gas field | The project was cancelled following the split of ConocoPhillips Company (oil and gas exploration and development) and Phillips 66 Company (midstream operations, refining and power generation) in April 2012. | http://www.globalccsinstitute.com/projects/12606
Texas Clean Energy Project "NowGen" | 2016-06-07 | Summit Power Group | Odessa | Texas | IGCC/polygen | 1.8mm TPY PRB to 400 MW(Gross) 710,000 TPY Ammonia/Urea | $2.5 billion | D - Delayed / Cancelled | Carbon capture rate of 90%, up to 3 million TPY for EOR in the west Texas Permian Basin and ultimate geologic sequestration. Transportation via existing pipelines. | In May 2016, it was announced that the US Department of Energy was on the verge of withdrawing funding for the project, which would effectively end the proposed plant's development. Summit Energy was given an opportunity to respond to a DOE report stating that money was continually poured into the project while deadlines were consistently missed and there were no guarantees of success. In December 2015, Summit Power Group announced a contract with China Huanqiu Contracting & Engineering Corp and SNC-Lavalin Engineers & Constructors. The contractcovers engineering, procurement, and construction of the carbon capture and chemical elements of the planned plant. This contract is considered to be a key milestone toward the development of the facility. CPS Energy has announced a new power purchase agreement with Summit Power to purchase power from the 400 MW IGCC plant presently under development. Under the new agreement, Summit Power will provide CPS with 200 MW of electricity from the new plant. Earlier in 2014, CPS withdrew from a prior power purchase agreement over concerns that power generated at the coal-fired facility would be too costly compared to power generated from abundant natural gas supplies. Project developers announced in April 2015 that they plan to break ground during the year on the proposed facility. The facility is anticipated to be commercially operational in 2018. | http://www.powermag.com/doe-poised-to-pull-out-of-texas-clean-energy-project/ http://www.pennenergy.com/articles/pennenergy/2014/10/cps-signs-ppa-with-coal-fueled-igcc-project-in-texas.html http://dailycaller.com/2014/01/13/epa-agenda-suffers-setback-as-clean-coal-plant-project-is-derailed/ http://fuelfix.com/blog/2015/04/01/odessa-coal-to-gas-power-plant-to-break-ground-this-year/ http://www.texascleanenergyproject.com/ http://www.texascleanenergyproject.com/?p=1344&preview=true
US Fuel CTL | 2015-12-15 | US Fuel Corporation | Perry County, Muhlenberg County | Kentucky | CTL | 300 tons of coal into 525 bpd liquid fuels including diesel and jet fuel | TBD | A - Active | Capture will be incorporated in the design but no specifics have been outlined. | US Fuel Corporation announced in April 2013 that Empyrean West had agreed to fund 65% of the loan cost for US Fuel's CTL facilities in Kentucky. US Fuel, upon completion of engineering work, intends to build multiple CTL facilities throughout the state. In April 2014, US Fuel Corporation announced a joint venture with Renewed World Energies (RWE) that would integrate RWE's bioreactor into US Fuel's planned coal-to-liquids plants in KY. | http://online.wsj.com/article/PR-CO-20130423-909106.html http://investorshangout.com/post/view?id=1321064
Wallula Energy Resource Center | 2014-06-13 | Wallula Resource Recovery,LLC & Edison Mission Group | Walla Walla | Washington | IGCC | 915 MW | $3.2 billion | D - Delayed / Cancelled | 65% sequestration | Delays in Batelle's testing of CO2 injectivity into Basalt and trouble obtaining the proper drilling equipment for a test well at WERC caused delays in early 2008 and the permits were retracted. WERC said they will continue research on CO2 injectivity into Basalt, but the IGCC power plant has been cancelled. | http://sequestration.mit.edu/tools/projects/wallula_energy_resource_center.html
Weirton Energy CTL Project | 2014-08-14 | Weirton Power | Weirton | West Virginia | CTL | Undetermined | TBD | D - Delayed / Cancelled | Not identified | Construction of a coal-to-liquids plant in Weirton could begin by the end of the year [2010], an official close to the project said. A man who claims to be on the verge of building a $2 billion coal-to-liquid plant in Weirton is wanted as a fugitive from Texas. If the [allegations] turn out to be true, "for all practical purposes, the energy plant is not likely to be a reality." It was later found that the allegations were true. One of Weirton Energy's directors Al Norman, was actually Albion Arlo Norman Jr. who had been convicted in US District Court of financial crimes related to the theft of $9.2 million from a cemetary association in New York. | http://www.weirtondailytimes.com/page/content.detail/id/557709/Coal-to-liquid-project-in-jeopar---.html http://www.wtrf.com/Global/story.asp?S=15853341 http://theintelligencer.net/page/content.detail/id/552289/Weirton-Still-Saddled-With-WSX-Properties.html?nav=5286
West Texas Renewable and Gas Monetisation Project | 2016-06-09 | D'Arcinoff Group | Hudspeth County | Texas | GTL | 30,000 bpd syngas to liquids, mostly jet fuel | $4.6 billion | A - Active | Not identified | In January 2016, The D'Arcinoff Group entered into an agreement with Wood Group Mustang that would have Wood Group Mustang provide primary engineering oversigth and technical services for the proposed facility. The D'Arcinoff Group,a US-based investment and alternative technology development company, plans to develop an integrated 30,000 barrels per day syngas-to-liquids facility, known as the West Texas Renewable and Gas Monetisation Project in Hudspeth County, Texas. The facility will primarily produce jet fuels. Amec Foster Wheeler announced it signed an agreement with D’Arcinoff Group to provide engineering and technical services for the facility. No timeline has been outlined for when construction will begin or when commercial operation is anticipated. D'Arcinoff Group has an agreement with GE Aviation to purchase 500,000 gallons of synthetic fuels annually to be used at GE's jet engine test facility in Ohio. The contract is set to begin in 2016. | http://www.amecfw.com/media/news-releases/2015/amec-foster-wheeler-awarded-syngas-to-liquids-project-in-the-us https://sites.google.com/a/darcinoff.com/dgwebsite/news/press-releases/dg-press-release-3-19-2013 http://biomassmagazine.com/articles/9659/ge-aviation-signs-purchase-agreement-for-biojet http://www.mustangeng.com/NewsandIndustryEvents/PressReleases/Pages/Wood-Group-appointed-as-owner%E2%80%99s-engineer-for-West-Texas-Renewable-and-Gas-Monetization-Project.aspx
WRI CTL Pilot | 2014-08-14 | Western Research Institute (WRI) |  | Wyoming | CTL | 1,000 barrels/day of low-sulfur diesel from 300 tons/day of Wyoming coal. Full-scale follow-up plant would convert 2,500 tons/day coal into 5,000 to 7,000 barrels/day liquid fuels. | TBD | A - Active | Pilot plant will be capable of capturing carbon dioxide, which will be converted to liquid form for use in the food industry or sold for EOR injection. | In a hearing before the Wyoming Legislature's Joint Minerals, Business, and Economic Development committee, Western Research Institute CEO Don Collins discussed proposed plans to developed a 1,000 barrel per day CTL pilot plant in Wyoming. The plant will be located on 5 acres, will be completed in 2016, and operate for 6 to 9 months to provide necessary information on whether the technology works. A full-scale plant, worth nearly $600 million and capable of producing 5,000 to 7,000 barrels per day would be the next step. | http://www.wyomingbusinessreport.com/article/20140617/NEWS/140619966/0/FRONTPAGE
ZeaChem BTL | 2015-06-01 | ZeaChem | Boardman | Oregon | BTL | Undefined amount of woody biomass and agricultural residues to 25 million gallons/yr of liquid fuel | $390.5 million | A - Active | Proprietary technology makes cellulosic ethanol using gasification and fermentation, emitting far less CO2 than other processes that convert cellulose to ethanol. | Zeachem's ethanol plant in Boardman, OR has scaled back operations and minimized it's workforce due to the lack of financing of a bridge-loan to carry the company through to it's next round of funding. In April 2015, Zeachem opened its Technology Institute and Processing Services to third parties interested in using Zeachem's equipment and personnel's experience to help these groups scale up their projects. | http://www.opb.org/news/blog/ecotrope/zeachem-halts-biofuel-production-in-boardman/ http://www.bizjournals.com/denver/blog/earth_to_power/2013/04/zeachem-scales-back-at-oregon-biofuel.html?page=all http://www.zeachem.com/press-releases/2015/4/21/zeachem-announces-technology-institute-processing-services