## Slide 1: Wabash CarbonSAFE DE-FE0031626
Christopher Korose
Steve Whittaker
University of Illinois
U.S. Department of Energy
National Energy Technology Laboratory
DE-FOA0001450 Kickoff Meeting
November 6, 2018

## Slide 2: Presentation Outline
Program Goals, Benefits, Project Objectives
Project Background/Methodology
  CO2 Source(s)
  Storage Complex
  Data Gaps and Acquisition
  Challenges
Organization/Communication
Task Breakdown
Milestones/Deliverables/Risks/Schedule
Summary

## Slide 3: Benefit to the Program
(DE-FOA-0001450) [The CarbonSAFE Initiative] addresses the following goals in DOE’s Carbon Storage R&D Program which have been established to support the scale-up and development of CCS leading to widespread deployment:
Develop and validate technologies to ensure 99 percent storage permanence.
Develop technologies to improve reservoir storage efficiency while ensuring containment effectiveness.
Support industry’s ability to predict CO2 storage capacity in geologic formations to within ±30 percent.
Develop best practice manuals for monitoring, verification, accounting (MVA), and assessment; site screening, selection, and initial characterization; public outreach; well management activities; and risk analysis and simulation.

## Slide 4: Wabash CarbonSAFE Overview: Project Objectives and Program Goals
Establish the feasibility of developing a commercial-scale geological storage complex near Terre Haute IN, that could store up to 50 million tonnes of industrially-sourced CO2.
  Address gap in knowledge around developing large-scale geological storage complexes
  Validate technologies to ensure 99% storage
  Validation of NRAP toolkits using field site data
  Improve storage capacity estimations for industry investment decision
  Contribute to best practice manuals to inform future commercialization efforts
Address technical and non-technical questions around developing commercial-scale storage complexes.
  Assess Public Outreach needs
  Analyze Regulatory Issues
  Characterize the Subsurface Storage Complex
  Construct Storage Complex Model
  Site Development Plan

## Slide 5: Benefit to the Program
Benefits Statement, Wabash CarbonSAFE
This project will determine the feasibility of developing a commercial-scale CCS project capable of storing over 50 million tonnes of anthropogenic CO2 in the U.S. Midwest. Wabash CarbonSAFE will demonstrate the transfer of technology to apply CCS to ammonia production thereby broadening the portfolio of industries that may benefit from integrating CCS into their operations. The project will address the development gap in upscaling CCS to commercial-scale as there are still are relatively few large carbon storage projects globally using deep saline reservoirs. Our work will address improving storage capacity estimates to attain an industry standard of ±30% or better for investment decisions. The data from this study will be used within the NRAP Toolkits to move toward validating technologies to ensure storage permanence and to improve reservoir storage efficiency. The project will determine the potential for transporting and utilizing CO2 for EOR in oil fields of the Illinois Basin. The knowledge gained will contribute to greater development of regional CCS assets, best practice manuals about CCS technology, and issues that will be of broad use to other sites and future commercialization efforts.

## Slide 6: Project Background Wabash CarbonSAFE
East sub-Basin Pre-Feasibility Project Number: DE-FE0029445
Build on East
sub-Basin work
Regional CO2 sources; focused reservoir/seal
characterization
Primary/secondary
areas of geological
interest
Macon County Feasibility
Project Number: DE-FE2900381
Wabash site
Macon Co. site

## Slide 7: CO2 Sources
Wabash Valley Resources (in development)
Pre-Feasibility CO2 sources screened for age, emissions, fuel; interest in participation
Wabash Valley Resources industrial site identified
Feasibility-partner discussions
began in August 2017
Proposed study submitted

## Slide 8: CO2 Source and Storage Wabash Valley Resources (WVR; formerly Quasar Syngas)
Site at former Wabash River Generating Station
IGCC Unit 1A (DOE 1993-1995)
Ownership changes, operations suspended (Nov ’15, ‘mothballed’)
WVR purchased plant May ’16 for ammonia production

## Slide 9: Wabash Valley Resources
Target 2021 operation
Petcoke -> syngas -> ammonia + H2 + CO2
>95% pure stream CO2 @ 1.7 million tonnes/yr
WVR business model: change plant design to maximize CO2 separation for storage or EOR sale
(45Q credits)
  65% -> 95% separation
Overview of process involving Rectisol that will be used by WVR to collect CO2 from the syngas stream.
Timeline for WVR development of ammonia and associated CO2 production.

## Slide 10: Wabash Valley Resources Feasibility Study
Evaluate CO2 stream/requirements, regulations, permitting; perform stakeholder analysis, further study WVR’s business case for CO2 storage
Assess CO2 transport
& EOR options from
WVR site toward
deeper IL Basin
Proximity of Wabash CarbonSAFE to Illinois Basin oilfields assessed for CO2 EOR.

## Slide 11: Background: Storage Complex
Mt. Simon Storage Capacity:
12 (E=0.4%) to 172 (E=5.5%) billion metric tons (2015)
Mt. Simon Sandstone reservoir/seals
Focus of primary-area pre-Feasibility work (and Macon well)
IBDP/IL-ICCS and other deep well logs & data…

## Slide 12: Mt. Simon Stratigraphy
Thick (>2,000 ft.) sandstone
Coastal, fluvial, eolian & dune deposits
Upper Mt. Simon: gas storage/waste
Best reservoir in lower Mt. Simon
  Ave 22% porosity
  K over 200md
Mt. Simon Sandstone
Alluvial
Fluvial
Eolian
Fluvial
Eolian
Tidal Flat
Dominant Depositional Environment
Upper
Middle
Lower
Argenta
Precambrian “Basement”

## Slide 13: Mt. Simon – Wabash Site
Few Mt. Simon penetrations in IL Basin
Regional thickness trend
Nearest well(s) to Wabash
  22mi N: upper Mt. Simon only
  25mi SE (upper), 50mi S (lower)
  75mi NW: arkosic zone @ Manlove
Lower Mt. Simon uncertain, stratigraphic well necessary
Mt. Simon Ss
  Porosity up to 25%
  K up to 600md

## Slide 14: Mt. Simon – Address Data Gaps
Synergy with other CarbonSAFE work in Macon and East Basin
Improve Basinwide understanding
Arkose
  From proximal Precambrian highs
  Basement structure
  Continuity to east?
New data will help prove this out
Regional thickness of highly arkosic zone in the lower Mt. Simon Sandstone (work in progress).

## Slide 15: Stratigraphic Test Well
Drill to ~8,300-8,500 ft depth
Collect core
  St. Peter?
  Eau Claire – Upper Mt. Simon
  Lower Mt. Simon
  Precambrian?
Sidewall core
Extensive logging suite
Well tests
Core Studies & Measurements

## Slide 16: 2D Seismic Acquisition
Tie-in site to region
  Formation continuity
  Geologic structures
Primarily on-road
2 x 10 miles

## Slide 17: Plume Modeling
50 MT CO2 plume size estimates (the maximum for each of 3 cases) circle the proposed Wabash well location.
Inset: simulation of CO2 injection into the Lower Mt. Simon Sandstone at the Wabash site;
CO2 saturation lateral extent is approximately 2.5 miles surrounding well (note vertical scale is exaggerated).
Lack of data
New data will inform modeling
  Static
  Dynamic
  NRAP
Reduce uncertainty
  Plume
  Storage
  Risk

## Slide 18: “Challenges”
Abandoned underground coal mines
  Adjust planned location of stratigraphic well
  Potential to affect eastern portion of 2D seismic
x

## Slide 19: “Challenges”
Well permitting
  Monitoring (VI) or waste injection (I) vs. stratigraphic test, plugged
  In conversation with IN DNR and US EPA
Industry & DOE timelines
CarbonSAFE
(II) 2 years
(III) 2 years (2022)
(IV) 3.5 years (2025)
Gather permit material…

## Slide 20: Expected Outcomes
Establish the feasibility of developing commercial-scale storage at Wabash Valley Resources’ site near Terre Haute, IN.
Obtain new geologic data to characterize, model, and better define the extent of the Lower Mt. Simon storage complex, decrease uncertainty, and improve regional understanding.
Assess the business and regulatory framework, risks, public sentiment, and regional infrastructure as part of a storage complex development plan.

## Slide 21: Organization Chart

## Slide 22: Communication Plan
The PI will conduct monthly meetings to ensure that project members understand the scope, goals, budget, milestones, deliverables, quality objectives, and contractual requirements of the project.
Adhere to Federal Assistance Reporting Checklist, and maintain effective communication between the Wabash CarbonSAFE team and DOE management.
The CCS Coordination Team will be responsible for formal internal and external lines of communication. A stand-alone communications plan outlining strategy and approach has been developed for communication management procedures (media contact, site visit procedures, partner communication guidelines, etc.)

## Slide 23: Task/Subtask Breakdown
Task 1.0 – Project Management and Planning
Task 2.0 – Risk Assessment and Monitoring
Task 3.0 – National Risk Assessment Partnership (NRAP) Screening
Task 4.0 – Stakeholder Engagement and Public Outreach
Task 5.0 – Business and Economic Development Assessment
Task 6.0 – Permitting and Compliance
Task 7.0 – Subsurface Characterization
Task 8.0 – Drilling and Well Testing
Task 9.0 – Storage Complex Modeling
Task 10.0 – Infrastructure Development
Task 11.0 – Storage Complex Development Planning

## Slide 24
Task 1.0 – Project Management and Planning
Subtask 1.1 – Manage all project activities, objectives, and milestones.
Subtask 1.2 – Project Management Plan.
Subtask 1.3 – Knowledge Sharing and Best Practices Manuals.
Subtask 1.4 – Communications.
Subtask 1.5 – Data Management.
Subtask 1.6 – Access to Geologic Materials/Samples.
(ISGS)
Task 2.0 – Risk Assessment and Monitoring
Subtask 2.1 – Risk Assessment.
Subtask 2.2 – Develop Risk Mitigation Strategy.
Subtask 2.3 – Identify Risk Pathways for Storage Complex Development.
(ISGS, PROJEO, PNNL)
Task 3.0 – National Risk Assessment Partnership (NRAP) Screening
Subtask 3.1 – NRAP Tookit Assessment.
(ISGS, PNNL)

## Slide 25
Task 4.0 – Stakeholder Engagement and Public Outreach
Subtask 4.1 – Conduct Stakeholder Analysis and Social Site Characterization.
Subtask 4.2 – Develop Stakeholder Engagement and Outreach Plan.
Subtask 4.3 – Develop Outreach Materials.
Subtask 4.4 – Conduct Stakeholder Engagement and Public Outreach.
Task 5.0 – Business and Economic Development Assessment
Subtask 5.1 – Business Development Case Study (evaluate saline storage and EOR scenarios).
Task 6.0 – Permitting and Compliance
Subtask 6.1 – Policy, Regulatory, Legal and Permitting Evaluation.
Subtask 6.2 – Obtain Permits for Phase 2 Activities.
Subtask 6.3 – Develop UIC Permitting Plan.
(ISGS, IU-SPEA, w/ WVR)
(ISGS, WVR)
(ISGS, WVR, GEOSTOCK, w/ Regulators)

## Slide 26
Task 7.0 – Subsurface Characterization
Subtask 7.1 – Pre-Drilling Site Assessment.
Subtask 7.2 –Evaluation of regional CO2 EOR potential.
Subtask 7.3 – Assess Data Collected from Stratigraphic Well.
Subtask 7.4 – Conduct Regional 2D Seismic Survey.
Subtask 7.5 – Integrate Well and Seismic Data into Geologic Models.
Subtask 7.6 –Identify Future Data Requirements.
(ISGS, IGWS, BYU, w/ PROJEO, GEOSTOCK)
Task 8.0 – Drilling and Well Testing
Subtask 8.1 – Design Well Drilling Program.
Subtask 8.2 – Conduct Drill on Paper Exercise.
Subtask 8.3 – Drill and Construct Stratigraphic Test Well.
Subtask 8.4 – Testing and Data Collection.
(GEOSTOCK, PROJEO, ISGS, IGWS)
Task 9.0 – Storage Complex Modeling
Subtask 9.1 – Development of Static Model.
Subtask 9.2 – Development of Dynamic Reservoir Model.
Subtask 9.3 – Development of Geomechanical Model.
Subtask 9.4 – Calibrate and Test Model Outputs.
(ISGS, PNNL, IGWS, GEOSTOCK)

## Slide 27
Task 10.0 – Infrastructure Development
Subtask 10.1 – CO2 Source Assessment.
Subtask 10.2 – Infrastructure and Transportation Assessment.
Subtask 10.3 – Develop Roadmap for Network and Storage Deployment.
(ISGS, TRIMERIC, IGWS, w/ WVR)
Task 11.0 – Storage Complex Development Planning
Subtask 11.1 – Detailed Site Characterization Plan.
Subtask 11.2 – Storage Commercialization Overview.
(ALL)

## Slide 28: Wabash CarbonSAFE: Success criteria
Address gap in knowledge around developing large-scale geological storage complexes
  The learnings from this effort are recorded in best-practice manuals
  Data is used within the NRAP toolkits
  Risk assessment and mitigation strategy documented
Assess Public Outreach needs
  Stakeholder analyses and Engagement and Outreach plan implemented
Analyze Regulatory Issues
  Permitting and Compliance Needs identified and Well Drilling Permit obtained
Analyze Business and Economic Issues
  Business Development Case Study performed, including potential for EOR
Characterize Subsurface Storage Complex
  Pre-drilling site assessment confirms well location
  Well is drilled with required data and samples being collected
Construct Storage Complex Model
  Static and dynamic models of site completed
Site Development Plan is completed
  The elements required for developing the commercial-scale storage site near Terre Haute, IN are identified and the workflow for proceeding is defined

## Slide 29: Milestones
Task / Subtask | ID | Milestone Title | Verification Method
1.0/1.1 | A | Project Kickoff Meeting | Attend Meeting, Presentation File
1.0/1.2 | B | Revised Project Management Plan | File provided to DOE
1.0/1.4 | C | Finalized Communication Plan | File provided to DOE
2.0/2.1 | D | Risk Assessment Summary | Summary in quarterly reports
3.0/3.1 | E | NRAP Assessment Report | File provided to DOE
4.0/4.2 | F | Stakeholder Engagement and Outreach Plan | File provided to DOE
5.0/5.1 | G | Business and Financial Case Study | File provided to DOE
6.0/6.2 | H | Obtain Stratigraphic Well Drilling Permit | Summary in quarterly reports
7.0/7.1 | I | Pre-Drilling Site Assessment | Attend Meeting
7.0/7.4 | J | Regional 2D Seismic Survey | Summary in quarterly reports
7.0/7.5 | K | Integrated Data for Modeling | Model output provided
8.0/8.2 | L | Drill on Paper Exercise | Attend Meeting
8.0/8.3 | M | Stratigraphic Test Well | Summary in quarterly reports
9.0/9.4 | N | Report on Modeling | Summary in quarterly reports
10.0/10.2 | O | 95% CO2 Separation Assessment | File provided to DOE
11.0/11.1 | P | Detailed Characterization Plan | File provided to DOE

## Slide 30: Deliverables
Task / Subtask | Deliverable
1.0/1.2 | Updated Project Management Plan
1.0/1.4 | Communication Plan
1.0/1.5 | Data Management Plan
1.0/1.6 | Catalog of Geologic Materials/Samples
2.0/2.2 | Risk Mitigation Plan
3.0/3.1 | NRAP Assessment Report
4.0/4.1 | Stakeholder Engagement Topical Report
5.0/5.1 | Business and Financial Case: storage and usage
6.0/6.1 | Regulatory, Legal, and Permitting Needs Case Study
7.0/7.2 | Evaluation of Regional CO2 EOR potential
8.0/8.4 | Geologic Material and Stratigraphic Test Well Report
9.0/9.4 | Report on Modeling
10.0/10.3 | Network and Expansion Roadmap
11.0/11.1 | Detailed Site Characterization Plan
11.0/11.2 | Integrated Regional Overview for Commercialization

## Slide 31: Risk Matrix

## Slide 32: Decision Points
Decision Point | Rationale | Success Criteria
Risk Assessment (2.1) | At each risk assessment determine and review risks to determine if moving forward is viable | Risks are determined to be manageable
Stakeholder Analysis (4.1) | Good stakeholder relations are critical path to successful development of Complex | Monitor, evaluate, and maintain transparent engagement
Pre-drilling Assessment (7.1) | Geologic assessment based on available data to be considered prior to initiating drilling | Suitable geology determined
Drill on Paper Exercise (8.2) | Drill on paper exercise used to walk through entire well, HSE, and other risk factors | Clear and achievable plan for drilling, risk management, HSE protocols
Dynamic Modeling/NRAP (9.2, 3.1) | Modeling results from reservoir model and NRAP assessment used to determine commercial viability of site | Model results show long-term storage potential, capacity estimates support modeling
Detailed Site Characterization Plan (11.1) | Characterization plan will be analyzed and prepared to determine if move to next Phase | Presence of viable stakeholder, geology, business, and regulatory pathways are present

## Slide 33: Proposed Schedule (1 of 2)
(continues)

## Slide 34: Proposed Schedule (2 of 2)
2018
2019
2020
S O N D
J A J O
J A J A

## Slide 35: Summary – Wabash CarbonSAFE
2-year study to assess commercial-scale CO2 storage feasibility at Wabash Valley Resources’ ammonia plant near Terre Haute, Indiana (planned operational 2021); CO2 source and storage location.
Evaluate site-specific saline storage along with regional EOR potential; conduct permitting, business, and stakeholder/social studies
Leverage CarbonSAFE team and build upon current projects
Characterize Mt. Simon storage complex: acquire new data, inform modeling and reduce uncertainties, improve understanding, and define the lower Mt. Simon storage complex for widespread CCS deployment in the IL Basin.