## Schedule
ALBANY BUILDING ASSESSMENT SCHEDULE
Date: | 2018-04-03
FIMS ASSET NUMBER | FIMS ASSET NAME | ASSESSING GROUP | PREVIOUS INSPECTION DATE | SCHEDULED ASSESSMENT DATE | COMPLETION DATE | COMMENTS | Frequency (Years) | Scheduled Date OVERRIDE
AOSF0019 | Transformer Stations | CAS | 2014-12-30 | 2017-01-28 | 2017-01-27 | --- | 3 | Yes - completed before new schedule
ABOO0027 | Building 27 | CAS | 2014-07-31 | 2017-02-16 | 2017-02-22 | Lab used for storage (if lab use, re-evaluate) | 4 | Yes - completed before new schedule
ABOO0013 | Building 13 | CAS | 2014-07-31 | 2017-02-28 | 2017-02-03 | --- | 5 | Yes - completed before new schedule
ABOO0024 | Building 24 | CAS | 2014-12-23 | 2017-03-17 | 2017-03-24 | --- | 3 | Yes - completed before new schedule
ABOO0031 | Building 31 | CAS | 2012-08-31 | 2017-04-30 | 2017-04-21 | Was on hold for renovation in 2016 | 4 | Yes - completed before new schedule
AOSF0013 | Security Fence | CAS | 2015-07-31 | 2017-05-31 | 2017-06-01 |  | 3 | Yes - completed before new schedule
ABOO0004 | Building 04 | CAS | 2014-10-30 | 2017-10-31 | 2017-11-17 | Inspected early October, 2 items needing investigation delayed the report being completed until mid November. October 2020 should still be the next inspection date. Item #8 on report pending ES&H testing of unknown flammable product. May take 2 months. Once more is known, the report will be updated again with the final solution on this issue. | 3
ABOO0017 | Building 17 | CAS | 2015-01-29 | 2018-01-31 | 2018-01-17 | --- | 3
ABOO0035 | Building 35 | CAS | 2015-02-28 | 2018-02-28 | 2018-03-20 | Report delayed approximately 20 days while determining final result for south exterior stair risers/ramp (attempted to install per modernization design, but later determined that scope should wait until full project goes forward, due mainly to top-of-concrete elevation TBD during major install of project). | 3
ABOO0019 | Building 19 | CAS | 2015-03-27 | 2018-03-31 | 2018-04-03 | --- | 3
AOSF0005 | Paved Parking Areas | CAS | 2015-06-26 | 2018-06-30 | 2018-08-17 | Report delayed due to extensive research for solutions | 3
AOSF0018 | Air Compressors - 100 psig | CAS | 2015-07-31 | 2018-07-31 | 2018-09-17 | Report delayed due to extensive research for solutions | 3
ABOO0018 | Building 18 | CAS | 2014-09-30 | 2018-09-30 | 2018-10-25 | Gas cylinder tank storage on west end makes this 4 years, not 5 | 4
ABOO0033 | Building 33 | CAS | 2014-10-30 | 2018-10-31 | 2018-10-11 |  | 4
ABOO0005 | Building 05 | CAS | 2014-11-30 | 2018-11-30 | 2018-11-20 | --- | 4
ABOO0029 | Building 29 | CAS | 2016-02-05 | 2019-01-31 | 2019-01-18 | --- | 3 | Yes - prevent multiple bldg's in 1 month
ABOO0028 | Building 28 | CAS | 2016-02-26 | 2019-02-28 | --- | --- | 3
ABOO0037 | Building 37 | CAS | 2015-03-27 | 2019-03-31 | --- | --- | 4
ABOO0030 | Building 30 | CAS | 2016-06-08 | 2019-04-30 | --- | --- | 3 | Yes - prevent multiple bldg's in 1 month
AOSF0026 | Storage Sheds | CAS | 2016-06-24 | 2019-05-31 | --- | 3-year frequency based on most critical sheds (chemicals/hazmat) | 3 | Yes - prevent multiple bldg's in 1 month
AOSF0020 | Fire Hydrants | CAS | 2016-06-24 | 2019-06-30 | --- | --- | 3
AOSF0001 | Secondary Roads | CAS | 2016-07-29 | 2019-07-31 | --- | --- | 3
ABOO0039 | Building 39 | CAS | 2015-09-28 | 2019-08-31 | --- | --- | 4 | Yes - prevent multiple bldg's in 1 month
ABOO0026 | Building 26 | CAS | 2016-12-20 | 2019-09-30 | --- | --- | 3 | Yes - prevent multiple bldg's in 1 month
ABOO0006 | Building 06 | CAS | 2014-12-23 | 2019-10-31 | --- | --- | 5 | Yes - prevent multiple bldg's in 1 month
ABOO0011 | Building 11 | CAS | 2014-12-23 | 2019-11-30 | --- | --- | 5 | Yes - prevent multiple bldg's in 1 month
AOSF0024 | Security Shack | CAS | 2015-12-22 | 2019-12-31 | --- | --- | 4
ABOO0036 | Building 36 | CAS | 2015-05-29 | 2020-01-31 | --- | Lab used for storage (if lab use, re-evaluate) | 5 | Yes - prevent multiple bldg's in 1 month
ABOO0021 | Building 21 | CAS | 2016-03-27 | 2020-02-29 | --- | --- | 4 | Yes - prevent multiple bldg's in 1 month
ABOO0020 | Building 20 | CAS | 2015-04-30 | 2020-02-29 | --- | --- | 5 | Yes - prevent multiple bldg's in 1 month
ABOO0001 | Building 01 | CAS | 2016-03-31 | 2020-03-31 | --- | --- | 4
AOSF0027 | Smoke Shacks | CAS | 2015-04-30 | 2020-04-30 | --- | --- | 5
ABOO0038 | Building 38 | CAS | 2015-05-29 | 2020-05-31 | --- | --- | 5
AOSF0006 | Paved Storage Areas | CAS | 2015-06-26 | 2020-06-30 | --- | Fenced-in storage areas on pavement | 5
ABOO0009 | Building 09 | CAS | 2015-10-28 | 2020-07-31 | --- | --- | 5 | Yes - prevent multiple bldg's in 1 month
ABOO0023 | Building 23 | CAS | 2016-10-28 | 2020-09-30 | --- | --- | 4 | Yes - prevent multiple bldg's in 1 month
ABOO0012 | Building 12 | CAS | 2015-11-27 | 2020-10-31 | --- | --- | 5 | Yes - prevent multiple bldg's in 1 month
ABOO0022 | Building 22 | CAS | 2016-12-12 | 2020-11-30 | --- | --- | 4 | Yes - prevent multiple bldg's in 1 month
ABOO0025 | Building 25 | CAS | 2016-12-13 | 2020-12-31 | --- | --- | 4
ABOO0007 | Building 07 | CAS | 2016-03-27 | 2021-02-28 | --- | --- | 5 | Yes - prevent multiple bldg's in 1 month
ABOO0032 | Building 32 | CAS | 2016-03-27 | 2021-03-31 | --- | --- | 5
ABOO0034 | Building 34 | CAS | 2016-04-29 | 2021-04-30 | --- | Lab w/ furnaces (lab not in use - if used, re-evaluate) | 5
AOSF0007 | Street Lighting | CAS | 2016-06-24 | 2021-06-30 | --- | --- | 5
AOSF0004 | Sidewalks | CAS | 2016-07-29 | 2021-07-31 | --- | --- | 5
ABOO0010 | Building 10 | CAS | 2016-11-29 | 2021-11-30 | --- | --- | 5
ABOO0008 | Building 08 | CAS | 2016-12-12 | 2021-12-31 | --- | --- | 5
ABOO0002 | Building 02 | CAS | 2010-09-01 | N/A | N/A | Up for demolition
AOSF0025 | Security Video Surveillance Sys. | Others | 2008-09-01 | Others | 2017-10-11 | ---
AOSF0017 | 100 psi Compressed Air Piping | PBPI | PBPI | PBPI | N/A | ---
AOSF0014 | 13 kV Electrical Lines - UG | PBPI | PBPI | PBPI | N/A | ---
AOSF0015 | 480v. Electrical Lines - UG | PBPI | PBPI | PBPI | N/A | ---
AOSF0012 | Fire Protection Water Piping | PBPI | PBPI | PBPI | N/A | ---
AOSF0021 | Fire Protection/ENS | PBPI | PBPI | PBPI | N/A | ---
AOSF0016 | Groundwater Monitoring Wells | PBPI | PBPI | PBPI | N/A | ---
AOSF0002 | Natural Gas Pipes | PBPI | PBPI | PBPI | N/A | ---
AOSF0010 | Potable Water Pipes | PBPI | PBPI | PBPI | N/A | ---
AOSF0009 | Sanitary Sewerage Pipes | PBPI | PBPI | PBPI | N/A | ---
AOSF0011 | Storm Water Sewer System | PBPI | PBPI | PBPI | N/A | ---
---
---

## Pivot
SCHEDULED ASSESSMENT DATE | FIMS ASSET NAME | PREVIOUS INSPECTION DATE | COMPLETION DATE
N/A | Building 02 | 2010-09-01 | N/A
Others | Security Video Surveillance Sys. | 2008-09-01 | N/A
PBPI | 100 psi Compressed Air Piping | PBPI | N/A
| 13 kV Electrical Lines - UG | PBPI | N/A
| 480v. Electrical Lines - UG | PBPI | N/A
| Fire Protection Water Piping | PBPI | N/A
| Fire Protection/ENS | PBPI | N/A
| Groundwater Monitoring Wells | PBPI | N/A
| Natural Gas Pipes | PBPI | N/A
| Potable Water Pipes | PBPI | N/A
| Sanitary Sewerage Pipes | PBPI | N/A
| Storm Water Sewer System | PBPI | N/A
2017-01-28 | Transformer Stations | 2014-12-30 | 2017-01-27
2017-02-16 | Building 27 | 2014-07-31 | 2017-02-22
2017-02-28 | Building 13 | 2014-07-31 | 2017-02-03
2017-03-17 | Building 24 | 2014-12-23 | 2017-03-24
2017-04-30 | Building 31 | 2012-08-31 | 2017-04-21
2017-05-31 | Security Fence | 2015-07-31 | ---
2017-10-31 | Building 04 | 2014-10-30 | ---
2018-01-31 | Building 17 | 2015-01-29 | ---
2018-02-28 | Building 35 | 2015-02-28 | ---
2018-03-31 | Building 19 | 2015-03-27 | ---
2018-06-30 | Paved Parking Areas | 2015-06-26 | ---
2018-07-31 | Air Compressors - 100 psig | 2015-07-31 | ---
2018-09-30 | Building 18 | 2014-09-30 | ---
2018-10-31 | Building 33 | 2014-10-30 | ---
2018-11-30 | Building 05 | 2014-11-30 | ---
2019-01-31 | Building 29 | 2016-02-05 | ---
2019-02-28 | Building 28 | 2016-02-26 | ---
2019-03-31 | Building 37 | 2015-03-27 | ---
2019-04-30 | Building 30 | 2016-06-08 | ---
2019-05-31 | Storage Sheds | 2016-06-24 | ---
2019-06-30 | Fire Hydrants | 2016-06-24 | ---
2019-07-31 | Secondary Roads | 2016-07-29 | ---
2019-08-31 | Building 39 | 2015-09-28 | ---
2019-09-30 | Building 26 | 2016-12-20 | ---
2019-10-31 | Building 06 | 2014-12-23 | ---
2019-11-30 | Building 11 | 2014-12-23 | ---
2019-12-31 | Security Shack | 2015-12-22 | ---
2020-01-31 | Building 36 | 2015-05-29 | ---
2020-02-29 | Building 20 | 2015-04-30 | ---
| Building 21 | 2016-03-27 | ---
2020-03-31 | Building 01 | 2016-03-31 | ---
2020-04-30 | Smoke Shacks | 2015-04-30 | ---
2020-05-31 | Building 38 | 2015-05-29 | ---
2020-06-30 | Paved Storage Areas | 2015-06-26 | ---
2020-07-31 | Building 09 | 2015-10-28 | ---
2020-09-30 | Building 23 | 2016-10-28 | ---
2020-10-31 | Building 12 | 2015-11-27 | ---
2020-11-30 | Building 22 | 2016-12-12 | ---
2020-12-31 | Building 25 | 2016-12-13 | ---
2021-02-28 | Building 07 | 2016-03-27 | ---
2021-03-31 | Building 32 | 2016-03-27 | ---
2021-04-30 | Building 34 | 2016-04-29 | ---
2021-06-30 | Street Lighting | 2016-06-24 | ---
2021-07-31 | Sidewalks | 2016-07-29 | ---
2021-11-30 | Building 10 | 2016-11-29 | ---
2021-12-31 | Building 08 | 2016-12-12 | ---
(blank) | (blank) | (blank) | (blank)