## Invoice Detail
NATIONAL ENERGY TECHNOLOGY LABORATORY
INVOICE/STAFFING DATA
1 Participant Name and Address |  |  | 4 Invoice No.: 0002
MY COMPANY, LLC |  |  | 5 Invoice Date: May 14, 2015
4567 Apple Lane |  |  | 6 Billing Period: April 1 - 30, 2015
Anywhere, WV 26505
2 Contract No.: DE-FE000400X
3 CLIN/SubCLIN/Task/Activity No. and Title: 0400X.200.01 - Project Management Support for the Natural Gas & Oil Program
[5 empty] | Current Period | [8 empty] | Cumulative
7 Name | 8 Labor Category (E N/E) or Description | 9 Status | 10 Employer | 11 Current Rate | 12 Hours Worked of Available | 13 Total Cost Current Period | 14 Total FTE Hours | 15 Labor by Site | [5 empty] | 16 Hours | 17 Prev Costs | 18 Current Cost
[8 empty] | Mgn | Pgh | Alb | Sugar Land | AK | Offsite
160
Pines, Barbara | Program Manager (E) | FT | MCL | 110 | 8 | 880 | 0.05 | 0.05 | [5 empty] | 12 | 440 | 1320
Little, Douglas | Senior Management Analyst (E) | FT | MCL | 95 | 16 | 1520 | 0.1 | 0.1 | [5 empty] | 24 | 760 | 2280
McGuire, Steve | Junior Management Analyst (E) | FT | MCL | 75 | 24 | 1800 | 0.15 |  | 0.15 |  |  |  |  | 36 | 900 | 2700
Walker, John | Engineer/Scientist 5 (E) | FT | JFC | 70 | 80 | 5600 | 0.5 | 0.25 | 0.25 |  |  |  |  | 120 | 2800 | 8400
Hope, Nadine | Business/Engineer Anlyst 3 (E) | FT | JFC | 64 | 64 | 4096 | 0.4 | [5 empty] | 0.4 | 96 | 2048 | 6144
Ford, Wade | Data Entry Operator 3 (N/E) | FT | MCL | 22.5 | 24 | 540 | 0.15 | [5 empty] | 0.15 | 36 | 270 | 810
| 19 DIRECT LABOR SUB-TOTAL: |  |  |  | 216 | 14436 | 1.35 | 0.4 | 0.4 | 0 | 0 | 0 | 0.55 | 324 | 7218 | 21654
| 20 LABOR G&A | 1.57% |  |  |  | 226.6452
| 21 TOTAL DIRECT LABOR |  |  |  |  | 14662.6452
|  | PLAN | ACTUAL
22 (Planned/Actual Labor hours - Current) |  | 216 | 216
23 (Planned/Actual Labor hours - Cumulative) |  | 324 | 318
24 Other Direct Costs (ODCs) | 25 Description
26 Subcontracts | BRD Consulting, Inc. |  |  |  |  | 340.5 | [8 empty] | 0 | 340.5
27 Materials | Office Supplies |  |  |  |  | 780 | [8 empty] | 500 | 1280
28 Travel | Steve McGuire |  |  |  |  | 1000 | [8 empty] | 0 | 1000
29 Training | PMI, Inc. |  |  |  |  | 1500 | [8 empty] | 1000 | 2500
30 Total ODCs | [5 empty] | 3620.5 | [8 empty] | 1500 | 5120.5
31 G&A |  | 8.5% |  |  |  | 307.7425 | [8 empty] | 270 | 577.7425
32 Fee | [5 empty] | 0 | [8 empty] | 0 | 0
33 Total Cost & Fee | [5 empty] | 18364.2425 | [8 empty] | 8988 | 27352.2425